## TEAM
RADIAN TEAM GANTT CHART | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Reacquaint team, review documentation, review subsystem work, and plan for the rest of 404
Order any final parts for subsystems | 2026-04-06: Not Started
Confirm that subystem is ready to integrate, if not, review and refine subsystem | 2026-04-06: In Progress
Bi-Weekly Presentation 1 | 2026-04-06: Completed
Integrate with Data and Wireless by confirming communication from Raspberry Pi to phone app | bar: 2026-02-02
Have all changes finished and updated for individual subsytems | bar: 2026-01-26 to 2026-02-09
Bi-Weekly Presentation 2 | bar: 2026-02-09
Integrate Physical with Data & Wireless by powering both Rasp. Pi and radar board independently of a power supply | bar: 2026-02-16
Integrate Data and Wireless to allow basic communication between two devices | bar: 2026-02-16
Design Blitz | bar: 2026-02-16
Test previous integration | bar: 2026-02-23
Bi-Weekly Presentation 3 | bar: 2026-02-23
Have all parts ordered and made for integration | bar: 2026-02-23
Integrate Physical with Data & Wireless by placing all components into housing | bar: 2026-02-23
Start falling and edgecase trials with Data and Radar, ensuring many trials of each case | bar: 2026-02-02 to 2026-03-09
Integrate Data with Wireless by communicating live data from radar to ML model | bar: 2026-02-23 to 2026-03-09
Test previous integration | bar: 2026-03-09 to 2026-03-16
Bi-Weekly Presentation 4 | bar: 2026-03-16 to 2026-03-30
Ensure all documentation is up to date | bar: 2026-03-16 to 2026-03-30
Start full system testing in accordance and in conjuction with Validation Plan | bar: 2026-03-23 to 2026-03-30
Bi-Weekly Presentation 5 | bar: 2026-03-30
Continue any debugging from full system testing | bar: 2026-03-23 to 2026-04-06
Retrain & improve fall detection accuracy to meet 90% requirement | bar: 2026-03-23 to 2026-04-06
Complete remaining validation tasks (Battery Life, Power Consumption, Autonomous Boot) | bar: 2026-03-30 to 2026-04-06
Final Presentation | bar: 2026-04-13
Final Demonstrations | bar: 2026-04-13
Engineering Project Showcase | bar: 2026-04-20
Final Report | bar: 2026-04-27
FOR UPDATE PRESENTATION #2
RADIAN TEAM GANTT CHART | 2026-01-26: 2026-02-16; 2026-02-02: 2026-02-23
Have all changes finished and updated for individual subsytems
Start falling and edgecase trials with Data and Radar, ensuring many trials of each case
Bi-Weekly Presentation 2
Integrate with Data and Wireless by confirming communication from Raspberry Pi to phone app | bar: 2026-01-26
Test previous integration | bar: 2026-01-26
Design Blitz | bar: 2026-01-26
Integrate Physical with Data & Wireless by powering both Rasp. Pi and radar board independently of a power supply | bar: 2026-02-02
Test previous integration | bar: 2026-02-02
Have all parts ordered and made for integration | bar: 2026-02-02
Integrate Data with Wireless by communicating live data from radar to ML model | bar: 2026-02-02
Bi-Weekly Presentation 3 | bar: 2026-02-02
FOR UPDATE PRESENTATION 4
RADIAN TEAM GANTT CHART | 2026-01-26: 2026-03-16; 2026-02-02: 2026-03-23; 2026-02-09: 2026-03-30; 2026-02-16: 2026-04-06; 2026-02-23: 2026-04-13
Start falling and edgecase trials with Data and Radar, ensuring many trials of each case | bar: 2026-01-26 to 2026-02-02
Integrate Data with Wireless by communicating live data from radar to ML model | bar: 2026-01-26 to 2026-02-02
Test previous integration | bar: 2026-02-02
Start full system testing in accordance and in conjuction with Validation Plan | bar: 2026-02-02
Continue any debugging from full system testing in conjuction with Validation Plan | bar: 2026-02-02 to 2026-02-16
Ensure all documentation is up to date | bar: 2026-02-09 to 2026-02-23

## MITCHELL
WIRELESS GANTT CHART | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Review the code for mobile app and radar to see where it was left off and decide what works still needs to be done and/or fixed. | 2026-03-30: Not Started
Debug and improve radar's data processing code | 2026-03-30: In Progress
Test alerts going to the mobile app, debug/improve from there | bar: 2026-02-02 to 2026-02-09
Begin to integrate with ML model and train with the radar's data | 2026-03-30: Completed
Validating radar data (filtering, tracking, etc.) | bar: 2026-02-16 to 2026-03-02
Completing falling and non-falling trials to gather data for various test cases | bar: 2026-02-23 to 2026-03-09

## MATTHEW
DATA GANTT CHART | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Review old subsytem and learn if it will be viable for integration | bar: 2026-01-12
Research updated ML model and learn how it will work differently than previous iteration | 2026-04-06: Not Started
Start coding new learning model for updated pipline | 2026-04-06: In Progress
Validate new CNN model with dummy data | 2026-04-06: Completed
Collect real training data for new CNN ML model using radar | bar: 2026-02-02 to 2026-03-09
Integrate with Wireless by sending a push notification from Raspberry Pi to moblie app using Gotify server | bar: 2026-02-16
Test previous integration | bar: 2026-02-16
Train first ML model and test it with other RADIAN recorded data | bar: 2026-02-16 to 2026-02-23
Integrate with Phyical by having Raspberry Pi be powered by the battery | bar: 2026-02-23
Test previous integration | bar: 2026-02-23
Train second iteration of ML model and test for accuracy | bar: 2026-02-23 to 2026-03-02
Train third iteration of ML model and test for accuracy | bar: 2026-03-02 to 2026-03-09
Test live action mode, simulating real working environment with ML model | bar: 2026-03-09 to 2026-03-23
Integrate with Physical by placing Raspberry Pi in enclosure | bar: 2026-03-23
Test previous integration | bar: 2026-03-23
Improve on model depending on previous test | bar: 2026-03-23 to 2026-04-06
Debug any Data issues regarding full system functionality | bar: 2026-03-30 to 2026-04-13
FOR UPDATE PRESENTATION 2
DATA GANTT CHART | 2026-01-12: 2026-02-02; 2026-01-19: 2026-02-09; 2026-01-26: 2026-02-16; 2026-02-02: 2026-02-23
Validate new CNN model with dummy data | bar: 2026-01-12
Collect real training data for new CNN ML model using radar | bar: 2026-01-12 to 2026-02-02
Integrate with Wireless by sending a push notification from Raspberry Pi to moblie app using Gotify server | bar: 2026-01-26
Test previous integration | bar: 2026-01-26
Train first ML model and test it with other RADIAN recorded data | bar: 2026-01-26 to 2026-02-02
Integrate with Phyical by having Raspberry Pi be powered by the battery | bar: 2026-02-02
Test previous integration | bar: 2026-02-02
FOR UPDATE PRESENTATION 3
DATA GANTT CHART | 2026-01-12: 2026-02-16; 2026-01-19: 2026-02-23; 2026-01-26: 2026-03-02; 2026-02-02: 2026-03-09
Validate new CNN model with dummy data | bar: 2026-01-12
Collect real training data for new CNN ML model using radar | bar: 2026-01-12 to 2026-02-02
Train first ML model and test it with other RADIAN recorded data | bar: 2026-01-12 to 2026-01-19
Integrate with Phyical by having Raspberry Pi be powered by the battery | bar: 2026-01-19
Test previous integration | bar: 2026-01-19
Train second iteration of ML model and test for accuracy | bar: 2026-01-19 to 2026-01-26
Train third iteration of ML model and test for accuracy | bar: 2026-01-26 to 2026-02-02
FOR UPDATE PRESENTATION 4
DATA GANTT CHART | 2026-01-12: 2026-03-16; 2026-01-19: 2026-03-23; 2026-01-26: 2026-03-30; 2026-02-02: 2026-04-06
Fix errors in integration from Wireless to Data (Pipeline from Radar to Raspberry Pi) | bar: 2026-01-12
Collect real training data for new CNN ML model using radar | bar: 2026-01-12 to 2026-01-19
Train second iteration of ML model and test for accuracy | bar: 2026-01-12
Train third iteration of ML model and test for accuracy | bar: 2026-01-19
Integrate with Physical by placing Raspberry Pi in enclosure | bar: 2026-01-19
Test previous integration | bar: 2026-01-19
Test live action mode, simulating real working environment with ML model | bar: 2026-01-19 to 2026-02-02
Improve on model depending on previous test | bar: 2026-01-26 to 2026-02-02
Debug any Data issues regarding full system functionality | bar: 2026-02-02

## WYATT
PHYSICAL GANTT CHART | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Complete PCB design and place order with JLCPCB | bar: 2026-01-12
Assemble PCB and test each subsystem (charger, protection, pack sweep, buck converter) | 2026-04-06: In Progress
Full system integration (charger + protection + buck) | 2026-04-06: Completed
Verify power supply stability under full system load: Raspberry Pi + radar sensor running complete algorithm and operational code | bar: 2026-02-09 to 2026-02-16
3D print enclosure and verify fit and alignment | bar: 2026-02-16
Revisit enclosure design | bar: 2026-02-23
Test report and slides | bar: 2026-02-23
Select and order RF transparent material | bar: 2026-02-23
Validate RF transparent material | bar: 2026-03-02 to 2026-03-09
Finalize and build demo fixture | bar: 2026-03-02 to 2026-03-09
End-to-end functional testing | bar: 2026-03-16
Validate radar performace in final setup | bar: 2026-03-16
Runtime / power verification in assembled system | bar: 2026-03-23
Fix any issues found during testing | bar: 2026-03-23 to 2026-03-30
Polish appearance of design | bar: 2026-03-30
Capture final data, plots, and photos | bar: 2026-03-30 to 2026-04-06
Prepare final documentation | bar: 2026-04-06 to 2026-04-13