## TEAM
RADIAN TEAM GANTT CHART | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-06
Establish team, team name, scope, and introductory plan to build the RADIAN system | bar: 2025-08-25 to 2025-09-01
Complete ConOps document, going over the general scope of the RADIAN system and how the RADIAN group plans to accomplish the goal | 2025-11-17: Not Started
Establish Radar, Raspberry Pi 3 ML Model, and and other needed components as functional | 2025-11-17: In Progress
Validation Plan, FSR, ICD, Milestones, 1st Presentation | 2025-11-17: Completed
Have each component working for intended subsystem, including radar given accurate data, a simple phone application UI, and a simple ML model running with dummy data | bar: 2025-09-22 to 2025-10-13
Order all components needed for the RADIAN system, including PCB, and any other needed components | bar: 2025-10-13 to 2025-10-20
Ensure that TI board can transmit and communicate to Raspberry Pi 3 | 2025-10-13: Pushed to 404
Ensure that all documentation is up to date up until this point | [16 empty] | ` | bar: 2025-10-20
2nd Presentation | bar: 2025-10-27
Start collecting ML model testing data using TI radar and ensure that all components can be powered via the Physical subsystem | bar: 2025-10-20 to 2025-11-17
Start small subsystem integration between Data and Wireless to test alert push notifications | bar: 2025-10-27 to 2025-11-17
Final Presentation | bar: 2025-11-17
Ensure that all subsystems are operating correctly within the scope of the RADIAN project | bar: 2025-11-03 to 2025-12-01
Final Demo | bar: 2025-12-01
Final Report | bar: 2025-11-24 to 2025-12-06

## MITCHELL
| 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01
Research on subsystem | bar: 2025-08-25 to 2025-09-01
Trade studies on component selection | bar: 2025-09-01 to 2025-09-08
Select radar and run demo of radar | 2025-11-17: Not Started
Select and install software for radar data processing | 2025-11-17: In Progress
Install software for mobile app development | 2025-11-17: Completed
Radar bring-up and data link setup | 2025-11-17: Behind Schedule
Radar to Pi integration | bar: 2025-10-06 to 2025-10-13
Gotify communication and app framework setup | bar: 2025-10-13 to 2025-10-27
Mobile app development | bar: 2025-10-06 to 2025-10-27
End to end testing (radar to pi, gotify to app) | bar: 2025-10-27 to 2025-11-17
System validation and documentation | bar: 2025-11-17 to 2025-11-24
Integration and Demo prep | bar: 2025-11-24 to 2025-12-01

## MATTHEW
| 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01
Requirements of the Data subsystem | 2025-11-17: Not Started
Trade studies and component selection | 2025-11-17: In Progress
Establish correct Raspberry Pi OS on component and establish a RADIAN GitHub | 2025-11-17: Completed
Research all connectivity between Raspberry Pi 3 and Android phone and select a communication protocol and server to communicate with phone application | 2025-11-17: Behind Schedule
Create simple decision tree ML model with dummy data, similar to potential parameters that will be used from the radar | bar: 2025-09-22 to 2025-09-29
Continue to refine decision tree ML model with accurate dummy data and start coding a random forest ML model | bar: 2025-09-29 to 2025-10-06
Small integration with Wireless to ensure that data can be transmitted from the TI board to the Raspberry Pi 3 | bar: 2025-10-06 to 2025-10-13
Search and select a potential data set to use for an ANN as well as to test the ML models | bar: 2025-10-06 to 2025-10-13
Start recording fall detection tests with RADIAN radar to train the ML model | bar: 2025-10-13 to 2025-11-17
Refine all simple ML models and continue to test accuracy of said models | bar: 2025-10-20 to 2025-10-27
Continue to update documentation as needed when continuing to test the Data subsystem | bar: 2025-09-15 to 2025-11-17
Start validation testing to establish reliability in the Data subsystem | bar: 2025-11-03 to 2025-11-17
Complete validation testing for Data subsystem | bar: 2025-11-17
Small integration with Wireless to ensure that the fall alert can be communicated to the phone application via Gotify's cloud servers | bar: 2025-11-17
Review all final documentation and make any needed edits | bar: 2025-11-24
Final adjustments and demo of Data subsystem | bar: 2025-12-01

## WYATT
WYATT'S GANTT CHART
| 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01
Research Power Requirements & Li-ion Cell Types: confirm loads, runtime, and safe cell options. | bar: 2025-08-25 to 2025-09-15
Requirements & Specs: Limits and pass/fail criteria. | 2025-11-17: Not Started
Battery Selection: choose cells/pack that meet the 4+ hr goal. | 2025-11-17: In Progress
Charger IC Selection & Setup: pick the charger and default limits. | 2025-11-17: Completed
Power Electronics Design (Schematic & PCB): capture, lay out, and label the power board. | 2025-11-17: Behind Schedule
Prototype Assembly: build Rev A and sanity-check power. | bar: 2025-10-06 to 2025-10-20
PCB validation: Have PCB in hand | bar: 2025-10-20 to 2025-10-27
Testing & Validation: run spec tests and record results. | bar: 2025-10-20 to 2025-10-27
Integration with Subsystems: mount, wire, and verify end-to-end alerts. | bar: 2025-10-20 to 2025-11-10
Documentation & Review: update ICD/FSR/BoM to match the build. | bar: 2025-11-10 to 2025-11-17
Final Adjustments & Submission: fix small issues and submit. | bar: 2025-11-24